## Day Plan
Job Alert Bot — Day-by-Day Plan (status as of 14 Sep 2026)
Date | Day | Task | What it covers | Status | Priority | Outcome / next check
2026-09-04 | Fri | Project setup | First working version: dashboard (React), API server, database, LinkedIn + Upwork scrapers connected, mock mode, basic scheduling. | Done | — | App ran; first real scraper runs succeeded.
2026-09-07 | Mon | Storage migration & hardening | Moved data from SQLite to MySQL; improved run pipeline and error messages. Old LinkedIn scraper's free trial expired — paid-actor errors discovered. | Done | — | Runs and errors recorded in history.
2026-09-14 | Mon | LinkedIn fixed end-to-end | Diagnosed 0-jobs cause; switched to curious_coder/linkedin-jobs-scraper; rebuilt search mapping (keywords, country, 24h/week/month window); verified with real runs. | Done | — | 23-26 real PHP Developer jobs per run; Telegram summary delivered.
2026-09-14 | Mon | Reliability fixes | Broken scrapers now show as failed runs (no more silent 0-jobs); retry storm capped; 10-min timeout; stuck 'running' runs auto-closed on restart; live status updates (~2s) with pulsing indicator. | Done | — | Verified via restart + live run.
2026-09-14 | Mon | Job browsing UI | Full job listing per run (list icon on every run card); job detail page (description, salary/budget, client info, apply link); clickable rows; raw job data saved per run. | Done | — | Built; final click-through verification pending (Sep 15).
2026-09-14 | Mon | Upwork diagnosis | Found why Upwork returns 0 jobs: one-time free trial quota exhausted, plus country filter mismatch (client country). Actor probed directly with/without location. | Done | — | Documented in PLAN.md; fix scheduled Sep 16-17.
2026-09-14 | Mon | Planning docs | Created PLAN.md (plain-language status + to-dos) and this day-by-day tracker. | Done | — | —
2026-09-15 | Tue | Publish the new UI | Run the production build (npm run build) so the job listing + detail pages appear on localhost:8787, not just the dev preview; click-test both pages with real run data. | Planned | High | Accept: pages visible at :8787, detail page renders a real job.
2026-09-16 | Wed | Apify account & billing | Add payment method to the Apify account (Upwork trial quota is exhausted and does not reset); confirm Upwork runs return jobs again; review LinkedIn concurrent-limit failures. | Planned | High | Accept: an Upwork run returns >0 jobs.
2026-09-17 | Thu | Upwork search fix | Make Upwork search worldwide (drop the client-country filter); keep country filtering for LinkedIn only; verify with a fresh run. | Planned | High | Accept: Upwork run returns relevant jobs.
2026-09-18 | Fri | Schedule spacing | Space out scheduled triggers so scrapers never run 5-at-once (free plan limit); confirm no more 'concurrent runs limit' failures. | Planned | Medium | Accept: a full scheduled day passes without 429 errors.
2026-09-21 | Mon | Login / signup | Add user accounts: sign-up flow, login screen, sessions. Prep per-user searches, schedules and Telegram settings. | Planned | High | Accept: dashboard requires login; new account can be created.
2026-09-22 | Tue | UI improvement pass | Layout and navigation polish, better empty states, clearer status colors, mobile-friendly responsive design across all pages. | Planned | Medium | Accept: pages consistent and usable on a phone-sized window.
2026-09-23 | Wed | Job detail enhancements | Polish the job detail page; add save/bookmark job and copy-link actions; verify every field renders for both LinkedIn and Upwork jobs. | Planned | Medium | Accept: bookmark survives reload.
2026-09-24 | Thu | Reliability extras | Show a distinct 'quota used up' status instead of a plain 0-jobs success; warn when attaching a duplicate schedule to a search; expire old seen-job records. | Planned | Medium | Accept: exhausted quota is obvious from the run card.
2026-09-25 | Fri | Docs cleanup | Update README (remove outdated CSV/SQLite claims and leftover merge text); keep PLAN.md and this tracker current. | Planned | Low | Accept: README matches reality.
Done = completed and verified. Planned = scheduled ahead (dates shift if priorities change). Details live in PLAN.md at the project root.

## Scrapers & Costs
Scrapers In Use — Actors & Pricing
Source | Apify actor | How it is priced | Free tier | Status today | Notes
LinkedIn | curious_coder/linkedin-jobs-scraper | Pay per result: about $1.00 per 1,000 job results. No monthly fee; heavier Apify plans lower the rate. A typical daily run (~25 jobs) costs well under a cent. | No actor-specific free tier. Account-level free plan caps at 5 actor runs at the same time. | Working | Verified 14 Sep: 23-26 real jobs per run, Telegram delivered.
Upwork | neatrat/upwork-job-scraper | Pay per result: about $3.20 per 1,000 jobs. Every run is billed a minimum of 10 jobs even if it finds none. | One-time trial: about 10 runs and 100 results in total. Does NOT reset monthly. Trial runs count even when they return zero jobs. | Quota exhausted | Returns 0 jobs until a payment method is added to the Apify account. Country filter means client country - worldwide search planned (Sep 17).
The Apify API key lives in the project's .env file (never share it). Scraper usage is billed by Apify directly - more frequent schedules = higher cost.